## Questions
QUESTIONS/RFI's & ANSWERS (Q&A)
Solicitation NO.: | FA301626Q0108
PROJECT NAME: | LAK FOC 149 FW
DATE: | 2026-08-19
CONTRACTOR: | TBD
NUMBER | QUESTIONS | SOW REFERENCE | GOVERNMENT RESPONSE | GOVERNMENT REFERENCE | DOES IT CHANGE SOW? Y/N
1 | Will all work areas require escort access? | 2.2.1 | Not all areas will require an escort excetpt for B935A which will require an escort from 502 CS. B930, 956, 957, 958 and any facilities in the controlled area (flightline) will require an escort from the 149th. | 149th FW Response | N
2 | Are there secure areas with special procedures? | 2.2.1 | For buildings and manholes near the flightline, prior coordination will need to be conducted/obtained through the 149th PM or 502d PM. This includes coordination for Manhole 205 (within construction zone for another project and will require prior coordination). | 149th FW Response | N
3 | Who will be our primary point of contact (POC) during construction? | N/A | AACOG POC, Chris Miller | N/A | N
4 | Are there any blackout dates or restricted work hours? | 5.3 Place of Performance Para 1.0 | The Contractor shall routinely work during normal duty hours M-F 0730 to 1630 hrs. However, mission requirements may necessitate work outside normal hours (nights and/or weekends), especially if existing service must be interrupted. Any site work requested outside of normal duty hours must be requested by the Contractor directly to the Contracting Officer, for approval. The Contracting Officer will consult with BCE on mission capability prior to approval of any unscheduled work. | SOW 5.3 Place of Performance Para 1.0 | N
5 | Are there any mission-critical periods that contractors should be aware of? | 5.3 and 5.4 | No mission-critical periods at this time; if this changes, 502d PM will inform contractor upon learning of the periods. | 502nd COM Squadron PM Response
6 | What are the expectations for work in areas that have experienced water intrusion or flooding? | 3.9 | For manholes with 12" of water or more, water will need to be pumped out by contractor. | 502nd SCOW Response | N
7 | Are there any restrictions on drilling or wall penetrations for new cable runs? | 2.3.3.10 | Nationally Recognized Testing Laboratory (NRTL)-rated fire assembly is required for penetrations through telecommunication space walls. For buildings 1147 & 1151 where wall penetration may be required, contractor may need to test for asbestos prior to drilling. | UFC 3-580-01 | N
8 | Are there existing utility maps identifying underground utilities that may interfere with trenching operations? | 2.3.3.11 | Will need to coordinate with 502 CES on Wednesdays to obtain locates and receive digging permits | N/A | N
9 | Are there any areas where trenching is prohibited or otherwise restricted? | 2.1.6 and 3.7 | Open trenching is not permitted across roadways, due to obstruction of traffic. Installation of duct bank infrastructure must be done via directional bore method. | SOW 3.8 Addition | Y
10 | Are there any existing non-operational cables that may be removed to accommodate the new installation? | 3.1 | No | N/A | N
11 | Are there any environmentally sensitive areas along the project route that require special consideration? | 2.1 | None | 502nd Environmental Response | N
12 | Are there any project-specific safety requirements beyond those contained in DAFMAN 91-203? | 2.1.2 | No additional safety requirements apply. | N/A | N
13 | Are there existing stormwater Best Management Practices (BMPs) that contractors must maintain or protect during construction? | 2.3.3.9 | 502nd CES maintains and inspects stormwater areas around the facilities occupied by the 149th. Contractor should contact 149 CES for Best Management Practices currently available. | N/A | N
14 | Where should soil testing samples be staged or stored during the project? | 2.3.3.9 | Per SOW 2.3.3.9 SD-09 Plans (Soil Testing), Based on characterization, soil must be transported to a disposal location approved by 502 Civil Engineering Squadron (CES). | SOW 2.3.3.9 | N
15 | Can JBSA provide photographs of the vault in Building 935, as well as Manholes (MH) 205 and 205A located near Air Traffic Control Tower Buildings 1143 and 1151? | 8.0 | 502 CS can provide requested pictures early next week of vault in B935 as well as MH-205 & MH-205A. Contractor will need to identify specific areas of the vault to capture in the photos. | N/A | N
16 | Under Section 3.1.3, Minimum Eligibility Requirements, respondents must demonstrate a minimum of three (3) years of experience. Does this requirement apply to the company as a whole, or may the experience of key personnel satisfy this requirement? Additionally, are any Texas contractor licenses required for this solicitation? | 3.1.3 | Per SOW 2.3.3.14 (A) At a minimum, the lead on-site installer will be BICSI certified for the work being performed (copper and/or fiber). The contractor shall provide the certification to the Contracting Officer no later than 5 business days after receipt of the award for 502CS PM approval. This Lead On-Site Installer can serve as the Site POC and shall be available during normal duty hours to meet on the installation within 1 hour with the CO or government PM to discuss problem areas. | SOW 2.3.3.14 | N
17 | Are there existing conduit systems and pathways from Building 935 to the other facilities identified in the project, or will conduit installation requirements be determined on a case-by-case basis or through individual task orders? | 4.0 and 8.0 | Exisisting Pathways are described within SOW 4.9 | SOW 4.9 | N
18 | Will an additional site visit be scheduled? If not, may a contractor that was unable to attend the scheduled site visit still submit a proposal in response to this solicitation? | N/A | There is only one site visit (SV). SV are not mandotary but encouraged. Respondents that did not attend the site visit remain eligible to submit a proposal, provided they meet all solicitation requirements. Proposals will be evaluated based on the information contained in the solicitation, all issued amendments, and the official Questions and Responses. | N/A | N
19 | Multiple sections of the solicitation refer to the fiber optic cable as "armored, shielded." Can JBSA confirm whether the intended product is all-dielectric fiber optic cable? | 1.0 and 4.9 | The contractor shall install OSP Dielectric fiber optic cable. | SoW Para 1.0-4.9 Revised | Y
20 | How far in advance must access and escort coordination occur for work near the munitions-adjacent buildings? Additionally, are there any special emissions control, RF, or other operational requirements that contractor personnel must observe while working in these areas? | 2.2.1 | 14 day advance notification is required for escort coordination due to explosive operations that would be occurring on a daily basis within Bldg 957. Bldg 956 is an administrative building that would just require escort coordination with same timeframe. | 149th FW Response | N
21 | Should the contractor utilize the previously scoped route between Building 1147 and Manhole (MH) 205 shown in the current Statement of Work, or is a different route, such as via Manhole (MH) 206, intended for this project? | 4.6 and 8.13 | Government recommends utilizing MH-206 for fiber route to Building 1147. | Revised SOW Figure 13 | Y
22 | Can JBSA provide the CVC/GeoBase existing infrastructure dataset (e.g., shapefile or CSV containing manhole and handhole coordinates) referenced in Section 3.26.3 to support pre-proposal route planning and geospatial submittal accuracy? | 2.26.3 | This is a submittal that the Contractor will provide the government. The government will be unable to provide the requested documents during solicitation. | Contracting Officer Response | N
23 | Please specify any additional emissions control, RF-silence, operational, or safety requirements applicable to work adjacent to the munitions storage buildings (Buildings 956 and 957) or the flightline (KMH220/KMH223), beyond the standard advance coordination and escort requirements. | 2.2 | For RF – silence, if any hotwork is required then it will have to be coordinated with Safety for approval. Operational wise for Bldg 957, 149th will need 2 week coordination due to explosives within the facility that will need to be removed. | 149th FW Response | N
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need wording that from the 149th FW of which building may require escorts
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Follow-up with the 149th FW for this answer.
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need to state yes or no on this question. I would recommend stating “No critical periods to disclose at this moment.” As this is a question we could discuss after contract award.
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add language in SOW 4.6 :" Note: Open trenching is not permitted. Installation of duct bank infrastructure must be done via directional bore method.”
Note on D26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SOW needs to be revised to reflect this change in every area where it mentions armor shielded
Note on D27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This Question Needs more specific answer. Galindo should reach out to environmental to see if there are any special requirements for these buildings. The Sam applies for question 23
Note on D28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SOW needs to reflect this change